## Leave Plan
Leave plan for Jan and Feb 2023
Month | Akash | Chandra | Akshit
2023-01-01 | 27th | NA | 27th
2023-02-01 | No plan for now | NA | 1 week (Date not confirmed)

## Task Status
Sr num | Task | Assigned to | Status
1 | Uncheck Functionality | Aakash | Done
2 | Form Validation - Dont submit Migration, until all fileds are present | Akshit | Done | testing pending
3 | Share the hardware and software requirements with CITI | Sonal | Done
4 | Once the entire batch is complete, send and email with both the configuration workbooks showing the end state | Aakash | Done
5 | Remove the hardcoded both the buttons ticked | Aakash | Done
6 | Status Success/Error for import and export process | Akshit/Chandra | Done
7 | send mail after forgot password is submitted | Akshit | Done
8 | 2 level of Approval - Aakash | Aakash | In progress
9 | Please check below issue, after submitting request, new record has been created dashboard(history) but no data available in request details popup(export_process_id) for the request | Aakash | Done
10 | API integration in application for Configuration workbook (source and target mails) | Omkar | pending | need API instead of calling from Oracle fusion we can call it from Config manager directly , it will decrease number of mail call from application
11 | Pagination on Dashboard table | Akshit | Done
12 | Naming convensions in code | Akshit | In progress
13 | Remove unnasarry data from Prod Database | Chandra | Done
14 | setup working Github in local machine | Akshit | Done
15 | Provide dump and setup local database in Akashit's system | Akshit/Chandra | Done
16 | UI CSS spacing in column as suggested by Sonal in both tables | Akshit | Done
17 | Migration Manager ->Request creation Form Request type value not setting properly issue | Akshit | Done
18 | For mail sending instaed of using hardcoded value from config.xml, use database fetched credentials from instance manager | Akash | Done
19 | Update Nesessory changes in Database for task number 18 | Chandra | Done
20 | DbQuery.js file update (Remove * with column name for each table) | Chandra | Done
21 | Oracle Database connection configuration with CITI | Chandra/Aakash | In progress
22 | Show/hide password feature on secured fields | Akshit | In progress
23 | API username password encryption/Decryption base64 | Akshit | In progress
24 | Accounting Hub Cloud Services (AHCS) configuration in mySQL application send requirnments for implementation to Sarang/Omkar | Yogesh | Done
25 | changes need to done on the basis of Oracle DB for CITI | Chandra | Not started
26
| check for oracle DB with Sonal and Minal | we do not have as confirmed with Minal , suggested to check with chandra | Chandra Checked with IT team for local installation, IT team is asking for client instance approval or licence BU is having
changes need to done on the basis of Oracle DB for CITI
Accounting Hub Cloud Services (AHCS) configuration in mySQL application
| CITI need api call payload for directly calling node without Angular | Aakash
| Send error to Sarang/Omkar import export api call | Yogesh | Done

## Create Instance
Create Instance Form
Instance Name - Text Field |  | Intance Type (LOV) | Environment Type (LOV)
URL - Text Field |  | ERP/SCM/PPM/HCM/CRM/ | DEV
Intance Type (LOV) |  | EPM | TEST
Environment Type (LOV) |  | RMCS | PROD
Username - Text Field
Password - Text Field
New Field ?
New Field ?
New Field ?
New Field ?
Submit (Button) | Cancel (Button)

## Migration Manager (Req Detail)
Migration Manager
Request Details |  |  |  |  | Task | Sub Task | Task-SubTask
Request Name | Text Field | Request Type (Multi-Select Check box) | Intance Type (LOV) | Offerings (LOV) | Initial Users | Run User and Roles Synchronization Process | Initial Users-Run User and Roles Synchronization Process
Request Type (Multi-Select Check box) | Generate Configuration Workbook | Generate Configuration Workbook | ERP/SCM/PPM/HCM/CRM/ | Financials | Initial Users | Manage Applications Security Preferences | Initial Users-Manage Applications Security Preferences
| Export & Import | Export & Import | EPM | Order Management | Initial Users | Import Users and Roles into Application Security | Initial Users-Import Users and Roles into Application Security
Intance Type (LOV) |  |  | RMCS | Procurement | Initial Users | Import User Login History | Initial Users-Import User Login History
Source Instance Name |  |  |  | Product Management | Initial Users | Create Implementation Users | Initial Users-Create Implementation Users
Destination Instance Name |  |  |  | Sales | Initial Users | Create Data Role for Implementation Users | Initial Users-Create Data Role for Implementation Users
Scheduling Time (Disabled Date & Time Filed) |  |  |  |  | Enterprise Profile | Establish Enterprise Structures | Enterprise Profile-Establish Enterprise Structures
[5 empty] | Enterprise Profile | Manage Reference Data Sets | Enterprise Profile-Manage Reference Data Sets
Offerings |  |  |  |  | Enterprise Profile | Manage Set Assignments for Set Determinant Type | Enterprise Profile-Manage Set Assignments for Set Determinant Type
Offerings (LOV) |  | Module (LOV) | Sub Module (LOV) | Task List | Enterprise Profile | Manage Reference Data Set Data Access for Users | Enterprise Profile-Manage Reference Data Set Data Access for Users
Module (LOV) |  | General Ledger | Ledger | Initial Users | Enterprise Profile | Manage Geographies | Enterprise Profile-Manage Geographies
Sub Module (LOV) |  | Accounts Payable | Business Unit | Enterprise Profile | Enterprise Profile | Load Geography Interface Data | Enterprise Profile-Load Geography Interface Data
Tasks |  | Cash Management |  | Legal Structures | Enterprise Profile | Run Geography Loader | Enterprise Profile-Run Geography Loader
Sub Tasks |  | Accounts Receivables |  | Financial Reporting Structures | Enterprise Profile | Run Maintain Geography Name Referencing | Enterprise Profile-Run Maintain Geography Name Referencing
|  | Fixed Assets |  | General Ledger | Enterprise Profile | Run Geocode Generation | Enterprise Profile-Run Geocode Generation
|  | Tax Management |  |  | Enterprise Profile | Manage Geography Lookups | Enterprise Profile-Manage Geography Lookups
|  | Common Tasks |  |  | Enterprise Profile | Manage Enterprise HCM Information | Enterprise Profile-Manage Enterprise HCM Information
|  | Inventory |  |  | Enterprise Profile | Manage Locations | Enterprise Profile-Manage Locations
|  | Self Service Procurement |  |  | Enterprise Profile | Manage Calendar Profile Option | Enterprise Profile-Manage Calendar Profile Option
|  | Purchasing |  |  | Enterprise Profile | Manage Data Warehouse Profile Option | Enterprise Profile-Manage Data Warehouse Profile Option
|  | Supplier Portal |  |  | Enterprise Profile | Manage Public Unique Identifier Profile Options | Enterprise Profile-Manage Public Unique Identifier Profile Options
|  | Sourcing |  |  | Legal Structures | Manage Legal Jurisdictions | Legal Structures-Manage Legal Jurisdictions
|  | Supplier Qualification |  |  | Legal Structures | Manage Legal Authorities | Legal Structures-Manage Legal Authorities
|  | Procurement Contracts |  |  | Legal Structures | Manage Legal Addresses | Legal Structures-Manage Legal Addresses
[5 empty] | Legal Structures | Manage Legal Entity Configurator Lookups | Legal Structures-Manage Legal Entity Configurator Lookups
[5 empty] | Legal Structures | Manage Legal Entity Configurator Descriptive Flexfield | Legal Structures-Manage Legal Entity Configurator Descriptive Flexfield
[5 empty] | Legal Structures | Manage Legal Entity Configurator Profile Options | Legal Structures-Manage Legal Entity Configurator Profile Options
[5 empty] | Legal Structures | Manage Legal Entity | Legal Structures-Manage Legal Entity
[5 empty] | Legal Structures | Manage Legal Entity Registrations | Legal Structures-Manage Legal Entity Registrations
[5 empty] | Legal Structures | Manage Intercompany Exceptions | Legal Structures-Manage Intercompany Exceptions
[5 empty] | Legal Structures | Manage Legal Entity Financial Information | Legal Structures-Manage Legal Entity Financial Information
[5 empty] | Legal Structures | Manage Legal Entity HCM Information | Legal Structures-Manage Legal Entity HCM Information
[5 empty] | Legal Structures | Manage Legal Entity Tax Profiles | Legal Structures-Manage Legal Entity Tax Profiles
[5 empty] | Legal Structures | Manage Legal Reporting Unit | Legal Structures-Manage Legal Reporting Unit
[5 empty] | Legal Structures | Manage Legal Reporting Unit Registrations | Legal Structures-Manage Legal Reporting Unit Registrations
[5 empty] | Legal Structures | Manage Associated Business Entities | Legal Structures-Manage Associated Business Entities
[5 empty] | Legal Structures | Manage Legal Reporting Unit Tax Profiles | Legal Structures-Manage Legal Reporting Unit Tax Profiles
[5 empty] | Legal Structures | Manage Legal Reporting Unit Financial Information | Legal Structures-Manage Legal Reporting Unit Financial Information
[5 empty] | Legal Structures | Manage Associated Balancing Segments | Legal Structures-Manage Associated Balancing Segments
[5 empty] | Financial Reporting Structures | Manage Chart of Accounts Value Sets | Financial Reporting Structures-Manage Chart of Accounts Value Sets
[5 empty] | Financial Reporting Structures | Manage Chart of Accounts Structures | Financial Reporting Structures-Manage Chart of Accounts Structures
[5 empty] | Financial Reporting Structures | Manage Chart of Accounts Structure Instances | Financial Reporting Structures-Manage Chart of Accounts Structure Instances
[5 empty] | Financial Reporting Structures | Manage Chart of Accounts Configurations | Financial Reporting Structures-Manage Chart of Accounts Configurations
[5 empty] | Financial Reporting Structures | Manage Chart of Accounts Value Set Values | Financial Reporting Structures-Manage Chart of Accounts Value Set Values
[5 empty] | Financial Reporting Structures | Manage Account Hierarchy Labels | Financial Reporting Structures-Manage Account Hierarchy Labels
[5 empty] | Financial Reporting Structures | Manage Account Hierarchies | Financial Reporting Structures-Manage Account Hierarchies
[5 empty] | Financial Reporting Structures | Publish Account Hierarchies | Financial Reporting Structures-Publish Account Hierarchies
[5 empty] | Financial Reporting Structures | Manage Account Combinations | Financial Reporting Structures-Manage Account Combinations
[5 empty] | Financial Reporting Structures | Manage Shorthand Aliases | Financial Reporting Structures-Manage Shorthand Aliases
[5 empty] | Financial Reporting Structures | Manage Segment Value Security Rules | Financial Reporting Structures-Manage Segment Value Security Rules
[5 empty] | Financial Reporting Structures | Manage Cross-Validation Rules | Financial Reporting Structures-Manage Cross-Validation Rules
[5 empty] | Financial Reporting Structures | Manage Chart of Accounts Mappings | Financial Reporting Structures-Manage Chart of Accounts Mappings
[5 empty] | Financial Reporting Structures | Manage Chart of Accounts Synchronization with DRM | Financial Reporting Structures-Manage Chart of Accounts Synchronization with DRM
[5 empty] | Financial Reporting Structures | Manage Messages for General Ledger | Financial Reporting Structures-Manage Messages for General Ledger
[5 empty] | Financial Reporting Structures | Manage Accounting Calendars | Financial Reporting Structures-Manage Accounting Calendars
[5 empty] | Financial Reporting Structures | Manage Transaction Calendars | Financial Reporting Structures-Manage Transaction Calendars
[5 empty] | Financial Reporting Structures | Manage Currencies | Financial Reporting Structures-Manage Currencies
[5 empty] | Financial Reporting Structures | Manage Conversion Rate Types | Financial Reporting Structures-Manage Conversion Rate Types
[5 empty] | Financial Reporting Structures | Manage Daily Rates | Financial Reporting Structures-Manage Daily Rates
[5 empty] | Financial Reporting Structures | Manage Currency Profile Options | Financial Reporting Structures-Manage Currency Profile Options
[5 empty] | General Ledger | Manage Primary Ledgers | General Ledger-Manage Primary Ledgers
[5 empty] | General Ledger | Assign Legal Entities | General Ledger-Assign Legal Entities
[5 empty] | General Ledger | Specify Ledger Options | General Ledger-Specify Ledger Options
[5 empty] | General Ledger | Assign Balancing Segment Values to Legal Entities | General Ledger-Assign Balancing Segment Values to Legal Entities
[5 empty] | General Ledger | Assign Balancing Segment Values to Ledger | General Ledger-Assign Balancing Segment Values to Ledger
[5 empty] | General Ledger | Manage Reporting Currencies | General Ledger-Manage Reporting Currencies
[5 empty] | General Ledger | Manage Secondary Ledgers | General Ledger-Manage Secondary Ledgers
[5 empty] | General Ledger | Specify Ledger Options | General Ledger-Specify Ledger Options
[5 empty] | General Ledger | Complete Primary to Secondary Ledger Mapping | General Ledger-Complete Primary to Secondary Ledger Mapping
[5 empty] | General Ledger | Assign Balancing Segment Values to Legal Entities | General Ledger-Assign Balancing Segment Values to Legal Entities
[5 empty] | General Ledger | Manage Reporting Currencies | General Ledger-Manage Reporting Currencies
[5 empty] | General Ledger | Assign Balancing Segment Values to Ledger | General Ledger-Assign Balancing Segment Values to Ledger
[5 empty] | General Ledger | Review and Submit Accounting Configuration | General Ledger-Review and Submit Accounting Configuration
[5 empty] | General Ledger | Manage Ledger Data Access for Users | General Ledger-Manage Ledger Data Access for Users
[5 empty] | General Ledger | Open First Period | General Ledger-Open First Period
[5 empty] | General Ledger | Manage Ledger Sets | General Ledger-Manage Ledger Sets
[5 empty] | General Ledger | Manage Data Access Sets | General Ledger-Manage Data Access Sets
[5 empty] | General Ledger | Manage Data Access Set Data Access for Users | General Ledger-Manage Data Access Set Data Access for Users
[5 empty] | General Ledger | Manage Accounting Automation | General Ledger-Manage Accounting Automation
[5 empty] | General Ledger | Manage Suspense Accounts | General Ledger-Manage Suspense Accounts
[5 empty] | General Ledger | Manage Statistical Units of Measure | General Ledger-Manage Statistical Units of Measure
[5 empty] | General Ledger | Manage Accounting and Reporting Sequences | General Ledger-Manage Accounting and Reporting Sequences
[5 empty] | General Ledger | Manage Journal Sources | General Ledger-Manage Journal Sources
[5 empty] | General Ledger | Manage Journal Categories | General Ledger-Manage Journal Categories
[5 empty] | General Ledger | Manage Journal Approval Rules | General Ledger-Manage Journal Approval Rules
[5 empty] | General Ledger | Manage AutoPost Criteria Sets | General Ledger-Manage AutoPost Criteria Sets
[5 empty] | General Ledger | Manage Journal Reversal Criteria Sets | General Ledger-Manage Journal Reversal Criteria Sets
[5 empty] | General Ledger | Manage Clearing Accounts Reconciliation | General Ledger-Manage Clearing Accounts Reconciliation
[5 empty] | General Ledger | Manage General Ledger Profile Options | General Ledger-Manage General Ledger Profile Options
[5 empty] | General Ledger | Manage General Ledger Descriptive Flexfields | General Ledger-Manage General Ledger Descriptive Flexfields
[5 empty] | General Ledger | Manage General Ledger Lookup Values | General Ledger-Manage General Ledger Lookup Values
[5 empty] | General Ledger | Manage Processing Schedules | General Ledger-Manage Processing Schedules
[5 empty] | General Ledger | Manage Storage Parameters | General Ledger-Manage Storage Parameters
[5 empty] | General Ledger | Run Optimization | General Ledger-Run Optimization
[5 empty] | General Ledger | Manage Allocations and Periodic Entries | General Ledger-Manage Allocations and Periodic Entries
[5 empty] | General Ledger | Manage Revaluations | General Ledger-Manage Revaluations
[5 empty] | General Ledger | Manage Close Monitor Setup | General Ledger-Manage Close Monitor Setup
[5 empty] | General Ledger | Complete Primary to Secondary Ledger Mapping | General Ledger-Complete Primary to Secondary Ledger Mapping
[5 empty] | General Ledger | Create Cross Validation Rules in Spreadsheet | General Ledger-Create Cross Validation Rules in Spreadsheet
[5 empty] | General Ledger | View Accounting Configuration Summary | General Ledger-View Accounting Configuration Summary

## Available on server
Sr num | Changes available for testing (http://140.238.166.54:4200/) | Date
1 | Form Validation - Dont submit Migration, until all fileds are present | 2023-02-02
2 | The uncheck functionality and Remove the hardcoded both the buttons ticked (Request type is editable in Migration Manager ->Request creation Form) | 2023-02-02
3 | Once the entire batch is complete, send and email with both the configuration workbooks showing the end state | 2023-02-02
4 | Status Success/Error for import and export process in request details | 2023-02-02
5 | send mail after forgot password is submitted and provide meaningful message instead of showing password in popup | 2023-02-02
6 | 2 level of Approval | 2023-02-02
7 | issue resolve - after submitting request, new record has been created dashboard(history) but no data available in request details popup(export_process_id) for the request after approval also | 2023-02-02
8 | Pagination has been added on Dashboard table | 2023-02-02

## Sheet1
Request | __>
html | Action
comp.ts
comp.services
| node (index.js) | route call shortform
route
| Services | will handle api call and db call
| Db | Api call
Response | <--